PROFESSIONAL COURSE SERIES

MARKETING PROJECT

MANAGEMENT

| LECTURE 02 | MARKETING PROJECT MANAGEMENT FUNDAMENTALS |
| --- | --- |

COURSE POSITIONING

Strategy  |  Governance  |  Delivery  |  Measurement  |  Applied Learning

| PREPARED FOR | Ahmed Labib |
| --- | --- |
| EDITION | Lecture-Based Professional Course |
| ISSUE DATE | July 2026 |

A standalone lecture from the premium Marketing Project Management professional course.

CONFIDENTIAL  |  PROFESSIONAL LEARNING MATERIAL

# LECTURE 02  |  MARKETING PROJECT MANAGEMENT FUNDAMENTALS

Turning marketing intent into controlled, measurable value delivery

| LECTURE 02 BRIEF ¦ 90 MINUTES |  |
| --- | --- |
| LEARNING OUTCOMES | 1. Define marketing project management as a governed value-delivery discipline. 2. Classify common marketing project archetypes and their complexity drivers. 3. Connect lifecycle stages, success dimensions and project-control requirements. |
| SESSION FLOW | 10 min definition ¦ 25 min project archetypes ¦ 25 min lifecycle and controls ¦ 20 min case exercise ¦ 10 min review |
| APPLIED OUTPUT | Marketing project archetype and success-criteria profile. |

## 2.1 Working definition

Marketing project management is the disciplined conversion of a defined marketing objective into an approved scope of work, a time-phased delivery plan, an accountable cross-functional team, a controlled budget, a measurement architecture and a documented decision trail. A marketing project is complete only when outputs are delivered, performance is assessed and lessons are captured—not merely when content is published.

## 2.2 Marketing project archetypes

| Archetype | Primary objective | Typical complexity drivers | Core deliverables |
| --- | --- | --- | --- |
| Product launch | Awareness, adoption and commercial readiness | Product dependencies, market timing, legal claims, channel coordination | Launch plan, messaging, landing pages, enablement, media assets, performance dashboard |
| Integrated campaign | Demand generation or brand activation | Multiple channels, creative variants, data tagging, approvals | Brief, media plan, content, automations, tracking plan, campaign report |
| Content / SEO program | Organic visibility and audience authority | Editorial capacity, search volatility, technical dependencies | Topic strategy, briefs, content calendar, technical actions, content performance |
| Lifecycle / email | Nurture, conversion, retention or reactivation | Segmentation, data quality, consent, automation logic | Journey map, segments, email sequence, tests, conversion report |
| Brand refresh | Repositioning and visual consistency | Stakeholder alignment, research, change adoption | Brand strategy, identity system, guidelines, rollout plan |
| Event / experience | Attendance, engagement, pipeline or advocacy | Vendors, venue, speakers, logistics, sponsorship, safety | Event plan, promotional assets, runbook, attendee data, post-event analysis |
| Marketing technology | Capability, automation or data improvement | Integration, privacy, migration, training and adoption | Requirements, configuration, testing, migration, governance, training |

## 2.3 Success dimensions

A modern marketing project should be evaluated across five dimensions. Optimizing only delivery efficiency can create campaigns that are on time and on budget but commercially ineffective; optimizing only performance can conceal uncontrolled rework, compliance exposure or unsustainable resource loading.

| Value OUTCOME Commercial and customer impact | Delivery CONTROL Scope, schedule and budget reliability | Quality EFFECTIVENESS Creative, technical and data standards | Risk ASSURANCE Compliance, brand and operational exposure | Learning ADAPTATION Tests, insights and reusable knowledge |
| --- | --- | --- | --- | --- |

## 2.4 Lifecycle and project controls

| Lifecycle stage | Key management question | Minimum control artifact |
| --- | --- | --- |
| Intake | Why should this project exist now? | Business case, project type, sponsor and prioritization score |
| Initiation | What is approved and who is accountable? | Project charter, stakeholders, high-level budget and success criteria |
| Planning | How will value be delivered and measured? | WBS, schedule, resource plan, risk register, measurement plan |
| Execution | Are teams producing approved deliverables? | Task workflow, quality checks, issue log, decisions and approvals |
| Monitoring and control | Are variance and risk within tolerance? | Status report, forecast, budget burn, change log, KPI dashboard |
| Launch / transition | Are release, compliance and operational-readiness criteria met? | Launch checklist, go/no-go approval, support plan |
| Closure and learning | What value was realized and what should change? | Post-mortem, benefits review, archive and reusable assets |

## Applied learning and assessment

| LECTURE 02 APPLICATION |  |
| --- | --- |
| APPLIED WORKSHOP | Choose a product launch, campaign, content program or website initiative. Define its objective, deliverables, constraints, lifecycle, success dimensions and the minimum controls required to manage it. |
| KNOWLEDGE CHECK | 1. What makes a marketing initiative a project rather than routine operations? 2. How do complexity drivers change the control approach? 3. Why must delivery success and business-outcome success be assessed separately? |