PROFESSIONAL COURSE SERIES

MARKETING PROJECT

MANAGEMENT

| LECTURE 03 | GOVERNANCE AND STRATEGIC ALIGNMENT |
| --- | --- |

COURSE POSITIONING

Strategy  |  Governance  |  Delivery  |  Measurement  |  Applied Learning

| PREPARED FOR | Ahmed Labib |
| --- | --- |
| EDITION | Lecture-Based Professional Course |
| ISSUE DATE | July 2026 |

A standalone lecture from the premium Marketing Project Management professional course.

CONFIDENTIAL  |  PROFESSIONAL LEARNING MATERIAL

# LECTURE 03  |  GOVERNANCE AND STRATEGIC ALIGNMENT

Ensuring every project has a defensible purpose, owner and decision path

| LECTURE 03 BRIEF ¦ 90 MINUTES |  |
| --- | --- |
| LEARNING OUTCOMES | 1. Translate strategic objectives into governed marketing project demand. 2. Apply intake, prioritization and stage-gate criteria across a project portfolio. 3. Define decision rights, escalation paths and accountable ownership. |
| SESSION FLOW | 10 min strategic alignment ¦ 25 min intake and gating ¦ 20 min prioritization ¦ 25 min portfolio workshop ¦ 10 min review |
| APPLIED OUTPUT | Portfolio intake, prioritization and decision-rights sheet. |

## 3.1 From request intake to approved portfolio

The source emphasizes alignment between marketing projects and business goals, but a scalable model needs a formal intake and prioritization mechanism. Without it, marketing teams become demand receivers, urgent requests displace strategic work, and resource plans lose credibility. [S1]

| Gate | Decision criteria | Approver | Output |
| --- | --- | --- | --- |
| G0 – Request validation | Defined problem, requester, target audience, due-date rationale and required decision | Marketing operations | Complete intake or return for clarification |
| G1 – Strategic fit | Contribution to enterprise objective, customer need and portfolio balance | Marketing leadership / sponsor | Prioritized concept |
| G2 – Feasibility | Capacity, budget, data, channel, technology, legal and dependency viability | Cross-functional review | Approved / deferred / rejected |
| G3 – Baseline approval | Scope, milestones, budget, risk, measurement and governance are complete | Sponsor / steering group | Authorized project baseline |
| G4 – Launch readiness | Quality, tracking, consent, disclosure, operational support and evidence are complete | Go/no-go authority | Launch authorization |
| G5 – Closure | Outputs accepted, data available, finances reconciled and learning captured | Sponsor and project manager | Formal closure and benefits follow-up |

## 3.2 Portfolio prioritization model

| Criterion | Suggested weight | Scoring guidance |
| --- | --- | --- |
| Strategic alignment | 25% | Directly supports a committed enterprise or business-unit priority. |
| Commercial / customer value | 20% | Expected revenue, margin, retention, advocacy, market or customer impact. |
| Urgency and timing | 15% | Market window, launch dependency, contractual commitment or regulatory date. |
| Evidence strength | 10% | Quality of customer insight, prior results, test data and causal hypothesis. |
| Feasibility | 10% | Availability of skills, technology, data, approvals and channel access. |
| Risk-adjusted effort | 10% | Complexity, uncertainty, compliance exposure and opportunity cost. |
| Learning value | 10% | Potential to validate a strategic assumption or create reusable knowledge. |

|  | GOVERNANCE PRINCIPLE A high-priority project must still satisfy minimum feasibility, compliance and measurement gates. Strategic urgency does not justify an unmeasurable or uncontrolled launch. |
| --- | --- |

## 3.3 Decision rights

| Decision | Accountable role | Required evidence |
| --- | --- | --- |
| Approve project initiation | Executive sponsor | Business case, priority score, initial budget and measurable outcome |
| Approve baseline | Sponsor / steering group | Charter, schedule, resource plan, risk and measurement plan |
| Approve scope change | Change authority | Impact on outcome, schedule, budget, resources, risk and dependencies |
| Approve campaign launch | Go/no-go authority | Quality, legal/privacy, tracking, support and contingency readiness |
| Stop or pivot campaign | Sponsor with channel / analytics owner | Performance evidence, risk threshold or changed business condition |
| Close project | Sponsor and project manager | Acceptance, financial reconciliation, archive and lessons learned |

## Applied learning and assessment

| LECTURE 03 APPLICATION |  |
| --- | --- |
| APPLIED WORKSHOP | Score three candidate marketing initiatives using strategic fit, expected value, urgency, risk, effort and capacity. Recommend approve, defer, redesign or reject, and assign the required decision authority. |
| KNOWLEDGE CHECK | 1. Why is a high-value idea not automatically a high-priority project? 2. Which decisions should remain with the sponsor rather than the project manager? 3. How do stage gates prevent low-quality demand from consuming capacity? |