PROFESSIONAL COURSE SERIES

MARKETING PROJECT

MANAGEMENT

| LECTURE 06 | FINANCIAL AND COMMERCIAL CONTROL |
| --- | --- |

COURSE POSITIONING

Strategy  |  Governance  |  Delivery  |  Measurement  |  Applied Learning

| PREPARED FOR | Ahmed Labib |
| --- | --- |
| EDITION | Lecture-Based Professional Course |
| ISSUE DATE | July 2026 |

A standalone lecture from the premium Marketing Project Management professional course.

CONFIDENTIAL  |  PROFESSIONAL LEARNING MATERIAL

# LECTURE 06  |  FINANCIAL AND COMMERCIAL CONTROL

Connecting campaign delivery to cost, profitability and benefits realization

| LECTURE 06 BRIEF ¦ 90 MINUTES |  |
| --- | --- |
| LEARNING OUTCOMES | 1. Build a complete cost baseline covering labor, media, vendors, technology and overhead. 2. Track actual cost, commitments, forecast-at-completion and budget burn. 3. Evaluate agency profitability and in-house projects using the appropriate value model. |
| SESSION FLOW | 10 min cost structure ¦ 25 min baseline and forecast ¦ 20 min profitability and value ¦ 25 min calculation workshop ¦ 10 min review |
| APPLIED OUTPUT | Financial control sheet with baseline, actuals, forecast and value case. |

## 6.1 Cost structure

| Cost category | Illustrative components | Control approach |
| --- | --- | --- |
| Internal labor | Strategy, creative, project management, analytics, engineering, review and administration. | Rate card or standard cost by role; planned versus actual hours. |
| Media | Paid search, social, display, sponsorship and promotion. | Committed spend, pacing, performance and reallocation rules. |
| Production | Video, photography, design adaptation, translation, print and physical assets. | Purchase orders, milestones, acceptance and change control. |
| Technology | Platforms, data services, integrations, automation and temporary tools. | License ownership, usage, renewal and implementation cost. |
| External services | Agency, freelancer, event, PR, legal and research fees. | Statement of work, deliverables, rate basis and acceptance. |
| Contingency | Known uncertainty and risk exposure. | Controlled reserve with defined approval authority. |

## 6.2 Budget baseline and forecast

Each project should have a time-phased cost baseline and an estimate at completion. A single total budget does not reveal whether overspend is occurring early, whether media is pacing correctly or whether remaining work can be completed within the authorized amount.

| Metric | Definition | Management use |
| --- | --- | --- |
| Budget at completion (BAC) | Approved total project budget. | Baseline authorization. |
| Actual cost (AC) | Cost incurred to the reporting date. | Spend visibility. |
| Committed cost | Approved obligations not yet invoiced or paid. | True remaining exposure. |
| Estimate to complete (ETC) | Forecast cost of remaining work. | Forward-looking control. |
| Estimate at completion (EAC) | AC + committed / remaining forecast, depending on model. | Expected final cost. |
| Budget variance | BAC − EAC. | Early escalation of projected overrun. |
| Budget burn rate | Spend or hours consumed relative to time and deliverable completion. | Detects front-loading, blocked work and scope growth. |

## 6.3 Agency profitability versus in-house value

| Operating context | Primary financial focus | Key measures |
| --- | --- | --- |
| Agency / professional services | Client and engagement profitability, utilization and revenue realization. | Gross margin, realization, write-offs, billable utilization, retainer burn, pipeline coverage. |
| In-house marketing | Incremental enterprise value and efficiency of constrained spend. | Contribution margin, pipeline value, customer acquisition economics, retention, cost avoidance, brand and strategic value. |
| Shared services / internal agency | Service economics plus business-unit value. | Chargeback, unit cost, SLA performance, internal satisfaction and outcome contribution. |

|  | FINANCIAL CONTROL PRINCIPLE Do not confuse delivery profitability with campaign effectiveness. Both must be visible: the cost and efficiency of producing the work, and the commercial or strategic value the work creates. |
| --- | --- |

## Applied learning and assessment

| LECTURE 06 APPLICATION |  |
| --- | --- |
| APPLIED WORKSHOP | Using a sample campaign budget, calculate committed cost, actual cost, estimate-to-complete, forecast-at-completion, variance and margin or value contribution. Identify the management action triggered by each variance. |
| KNOWLEDGE CHECK | 1. Why are commitments as important as paid invoices? 2. How does agency margin analysis differ from an in-house benefits case? 3. What does budget burn reveal when schedule progress is considered at the same time? |