PROFESSIONAL COURSE SERIES

MARKETING PROJECT

MANAGEMENT

| LECTURE 07 | MEASUREMENT AND ANALYTICS |
| --- | --- |

COURSE POSITIONING

Strategy  |  Governance  |  Delivery  |  Measurement  |  Applied Learning

| PREPARED FOR | Ahmed Labib |
| --- | --- |
| EDITION | Lecture-Based Professional Course |
| ISSUE DATE | July 2026 |

A standalone lecture from the premium Marketing Project Management professional course.

CONFIDENTIAL  |  PROFESSIONAL LEARNING MATERIAL

# LECTURE 07  |  MEASUREMENT AND ANALYTICS

Building an auditable path from project activity to business value

| LECTURE 07 BRIEF ¦ 90 MINUTES |  |
| --- | --- |
| LEARNING OUTCOMES | 1. Design a measurement plan before campaign build and launch. 2. Create a KPI hierarchy spanning delivery, output, outcome and business value. 3. Select attribution or incrementality methods appropriate to the decision and data maturity. |
| SESSION FLOW | 10 min measurement architecture ¦ 25 min KPI design ¦ 20 min attribution ¦ 25 min KPI-tree workshop ¦ 10 min review |
| APPLIED OUTPUT | Measurement plan, KPI dictionary and dashboard blueprint. |

Figure 1 — Recommended KPI hierarchy for governed marketing project management.

## 7.1 Measurement plan

The source identifies lead generation, lead conversion, utilization and profit margin as example metrics, but a comprehensive system must define exactly how data is created, validated and interpreted. [S1] Google Analytics guidance illustrates the need to identify meaningful events, classify important outcomes as key events and govern how those events feed reporting and attribution. [R2]

| Measurement-plan field | Required definition |
| --- | --- |
| Business question | The decision the metric must support. |
| Metric and formula | Precise definition, numerator, denominator, exclusions and currency/time basis. |
| Baseline and target | Current state, target value, target date and confidence level. |
| Event / data source | System, event name, parameters, source owner and collection method. |
| Attribution / causality | How credit is assigned and what the model cannot prove. |
| Segmentation | Audience, market, product, channel, creative, lifecycle stage or cohort. |
| Frequency and latency | Real-time, daily, weekly, monthly and expected data delay. |
| Data quality checks | Completeness, duplication, invalid traffic, consent and reconciliation rules. |
| Owner and action threshold | Accountable owner, tolerance, alert trigger and required response. |

## 7.2 KPI classes

| KPI class | Examples | Caution |
| --- | --- | --- |
| Business outcomes | Revenue, contribution margin, market share, customer lifetime value, retention. | Often affected by multiple non-marketing factors. |
| Marketing outcomes | Qualified pipeline, conversion, incremental sales, brand lift, share of search. | Requires consistent definitions and causal humility. |
| Campaign metrics | Reach quality, engagement, CTR, cost per result, ROAS, frequency, completion rate. | May reward platform behavior without proving enterprise value. |
| Project controls | Milestone variance, schedule reliability, cost variance, cycle time, rework, approval latency. | Measures delivery health, not campaign effectiveness. |
| Data quality | Tag coverage, event validity, identity match, consent rate, source completeness. | Poor data can make every downstream metric unreliable. |
| Learning metrics | Hypotheses tested, decision velocity, reusable insights, test confidence. | Quantity of tests is not equivalent to learning quality. |

## 7.3 Attribution and incrementality

Attribution allocates observed credit; it does not automatically establish causal impact. Marketing leaders should distinguish platform-reported attribution from independent analytics, matched-market or holdout tests, lift studies and broader commercial evidence. The appropriate method depends on decision value, data availability, risk and cost.

| Method | Best use | Principal limitation |
| --- | --- | --- |
| Rule-based attribution | Operational reporting and transparent channel comparison. | Sensitive to the selected rule and customer-journey visibility. |
| Data-driven attribution | Large datasets with stable event collection. | Model opacity and dependence on platform data. |
| Marketing mix modeling | Strategic budget allocation across channels and time. | Requires sufficient history and statistical expertise. |
| Incrementality / holdout testing | Estimating causal lift for a specific intervention. | Operational complexity and potential sample-size constraints. |
| Brand lift / research | Awareness, consideration and perception effects. | Survey design, cost and response bias. |
| Qualitative evidence | Complex B2B journeys, strategic accounts and new-category learning. | Not directly scalable or fully attributable. |

|  | DASHBOARD DESIGN RULE Every executive dashboard should show outcomes, forecast, delivery variance, data quality and required decisions—not only historical campaign metrics. |
| --- | --- |

## Applied learning and assessment

| LECTURE 07 APPLICATION |  |
| --- | --- |
| APPLIED WORKSHOP | Build a KPI tree for one marketing project. For each KPI define formula, owner, data source, frequency, target, decision threshold and known limitation. Add a practical attribution or incrementality approach. |
| KNOWLEDGE CHECK | 1. Why should output metrics not be treated as business outcomes? 2. What makes a KPI auditable and decision-useful? 3. When is experimental incrementality preferable to multi-touch attribution? |