PROFESSIONAL COURSE SERIES

MARKETING PROJECT

MANAGEMENT

| LECTURE 08 | RISK, COMPLIANCE AND AI GOVERNANCE |
| --- | --- |

COURSE POSITIONING

Strategy  |  Governance  |  Delivery  |  Measurement  |  Applied Learning

| PREPARED FOR | Ahmed Labib |
| --- | --- |
| EDITION | Lecture-Based Professional Course |
| ISSUE DATE | July 2026 |

A standalone lecture from the premium Marketing Project Management professional course.

CONFIDENTIAL  |  PROFESSIONAL LEARNING MATERIAL

# LECTURE 08  |  RISK, COMPLIANCE AND AI GOVERNANCE

Embedding assurance into the workflow instead of adding it after production

| LECTURE 08 BRIEF ¦ 90 MINUTES |  |
| --- | --- |
| LEARNING OUTCOMES | 1. Identify, assess, assign and monitor project and campaign risks. 2. Embed privacy, consent, disclosure, claims and rights controls into stage gates. 3. Apply responsible-AI controls covering data, human review, provenance and accountability. |
| SESSION FLOW | 10 min risk framework ¦ 25 min compliance controls ¦ 20 min AI governance ¦ 25 min risk-register workshop ¦ 10 min review |
| APPLIED OUTPUT | Risk register, compliance checklist and AI approval gate. |

## 8.1 Risk management framework

The source describes avoidance, reduction, transfer and acceptance as common responses. [S1] A complete risk process also requires identification, probability and impact assessment, ownership, response deadlines, residual-risk evaluation and escalation thresholds.

| Risk category | Illustrative exposure | Typical controls |
| --- | --- | --- |
| Strategic | Campaign does not support priority or customer need. | Business case, portfolio gate, hypothesis and sponsor review. |
| Scope / schedule | Late additions, approval delays, unrealistic dates. | Baseline, change control, approval SLA and dependency tracking. |
| Resource | Critical skill shortage, overload or vendor failure. | Capacity plan, back-up owner, WIP limits and contingency vendor. |
| Financial | Budget burn, media inefficiency, unplanned production cost. | Time-phased budget, forecast, commitment log and reallocation rules. |
| Data / analytics | Broken tags, poor consent, invalid attribution or data latency. | Measurement specification, QA, reconciliation and data-owner sign-off. |
| Legal / regulatory | Misleading claims, missing disclosures, privacy or usage-rights failure. | Legal review, disclosure checklist, consent design and evidence archive. |
| Brand / quality | Inconsistent creative, factual error, cultural harm or accessibility issue. | Brand QA, factual review, localization and accessibility checklist. |
| Technology / cyber | Integration failure, unauthorized access or platform outage. | Testing, permissions, back-up process and incident plan. |
| AI / model risk | Hallucinated facts, undisclosed synthetic content, data leakage or bias. | Approved use cases, human review, provenance, restricted data and evaluation. |

## 8.2 Disclosure and privacy controls

The FTC advises that material relationships in endorsements should be disclosed clearly and conspicuously with the endorsement itself, not hidden in a profile or behind additional clicks. [R3] The exact legal framework varies by jurisdiction, but the project workflow should always make the disclosure decision, wording, placement and approval evidence explicit.

| Control point | Minimum requirement |
| --- | --- |
| Data collection | Approved purpose, lawful basis / consent as applicable, defined retention and access. |
| Audience and targeting | Permitted attributes, exclusion rules, sensitive-data restrictions and platform terms. |
| Cookies and tracking | Consent behavior, tag firing rules, regional configuration and evidence of testing. |
| Endorsements and creators | Material relationship identified, disclosure approved and placement validated. |
| Claims and substantiation | Objective claims supported by retained evidence and approved wording. |
| Rights and licensing | Usage rights for images, music, testimonials, data and generated assets. |
| Accessibility | Content, landing pages, documents and media meet applicable accessibility requirements. |
| Records | Final assets, approvals, disclosures, test evidence and key decisions archived. |

## 8.3 Responsible AI controls

NIST’s AI Risk Management Framework and Playbook organize AI risk management around Govern, Map, Measure and Manage. [R1] For marketing teams, these functions can be translated into practical workflow controls rather than a separate policy document.

| NIST-aligned function | Marketing implementation |
| --- | --- |
| Govern | Approved AI use cases, accountable owner, training, restricted data, supplier requirements and incident escalation. |
| Map | Document the audience, task, model, content type, risk context, affected stakeholders and potential harm. |
| Measure | Evaluate factual accuracy, bias, brand alignment, privacy, originality, disclosure needs and output reliability. |
| Manage | Apply human approval, revise or reject outputs, record provenance, monitor incidents and improve controls. |

|  | AI RELEASE GATE No AI-generated output should be published solely because it is fast or grammatically polished. The accountable human owner must verify facts, rights, claims, audience suitability, disclosure obligations and brand standards. |
| --- | --- |

## Applied learning and assessment

| LECTURE 08 APPLICATION |  |
| --- | --- |
| APPLIED WORKSHOP | Create a risk register for a data-driven campaign using probability, impact, owner, response, trigger and residual risk. Add privacy, disclosure, intellectual-property and generative-AI approval checks to the launch gate. |
| KNOWLEDGE CHECK | 1. What is the difference between a risk response and a contingency action? 2. Which compliance controls must be designed before content production? 3. Why does human review not remove the need for AI provenance and accountability? |