PROFESSIONAL COURSE SERIES

MARKETING PROJECT

MANAGEMENT

| LECTURE 09 | STAKEHOLDER COMMUNICATION AND COLLABORATION |
| --- | --- |

COURSE POSITIONING

Strategy  |  Governance  |  Delivery  |  Measurement  |  Applied Learning

| PREPARED FOR | Ahmed Labib |
| --- | --- |
| EDITION | Lecture-Based Professional Course |
| ISSUE DATE | July 2026 |

A standalone lecture from the premium Marketing Project Management professional course.

CONFIDENTIAL  |  PROFESSIONAL LEARNING MATERIAL

# LECTURE 09  |  STAKEHOLDER COMMUNICATION AND COLLABORATION

Creating decision velocity, transparency and disciplined escalation

| LECTURE 09 BRIEF ¦ 90 MINUTES |  |
| --- | --- |
| LEARNING OUTCOMES | 1. Map stakeholder interest, influence, information needs and decision authority. 2. Design a communication cadence that supports action rather than reporting volume. 3. Produce a concise status report with decisions, exceptions and escalation triggers. |
| SESSION FLOW | 10 min stakeholder architecture ¦ 20 min RACI and authority ¦ 20 min cadence ¦ 30 min status-report workshop ¦ 10 min review |
| APPLIED OUTPUT | Stakeholder map, RACI, communication plan and one-page status report. |

## 9.1 Stakeholder architecture

| Stakeholder group | Primary interest | Required engagement |
| --- | --- | --- |
| Executive sponsor | Business outcome, risk, investment and strategic alignment. | Decision-focused updates, forecast, exceptions and recommendations. |
| Marketing leadership | Portfolio balance, capability and brand / channel performance. | Portfolio review and resource trade-offs. |
| Project team | Requirements, priorities, dependencies and fast decisions. | Daily workflow visibility and short operational cadence. |
| Sales / product / operations | Launch readiness, lead handling, product claims and customer experience. | Joint milestones, acceptance and transition planning. |
| Analytics / RevOps | Tracking, attribution, data quality and reporting. | Early design involvement and QA sign-off. |
| Legal / privacy / security | Claims, data use, rights, disclosures and risk tolerance. | Risk-based review with agreed turnaround times. |
| Finance / procurement | Budget, commitments, vendor terms and value realization. | Forecast, PO / contract controls and closure reconciliation. |
| Client / external partner | Scope, approvals, deliverables, dependencies and feedback. | Shared status, formal decisions and documented change control. |

## 9.2 Communication cadence

| Forum | Cadence | Purpose | Output |
| --- | --- | --- | --- |
| Delivery stand-up | Daily or 2–3 times weekly | Blockers, priorities and immediate dependencies. | Updated tasks and issue ownership. |
| Project status review | Weekly | Progress, forecast, budget, risk and decisions. | One-page status report and action log. |
| Creative / technical review | By milestone | Quality, consistency, feasibility and acceptance. | Approved deliverable or revision actions. |
| Steering review | Biweekly or monthly | Exceptions, trade-offs, scope changes and strategic alignment. | Decisions and revised direction. |
| Performance optimization | Weekly / campaign-specific | Channel results, tests and budget shifts. | Optimization actions and updated forecast. |
| Post-mortem | Within 1–2 weeks of closure | Outcome, delivery, root causes and reusable learning. | Lessons log and process improvements. |

## 9.3 One-page status report

| Section | Required content |
| --- | --- |
| Overall status | RAG status with a one-sentence rationale. |
| Outcome and scope | Objective, approved scope and any pending change. |
| Milestones | Baseline, current forecast and variance. |
| Budget | Budget, actual, committed, EAC and variance. |
| Performance | Outcome KPIs, leading indicators and data-quality note. |
| Top risks / issues | Owner, response, due date and residual exposure. |
| Decisions required | Decision, options, recommendation and deadline. |
| Next period | Critical deliverables and stakeholder obligations. |

## Applied learning and assessment

| LECTURE 09 APPLICATION |  |
| --- | --- |
| APPLIED WORKSHOP | Prepare a RACI and one-page status report for a delayed campaign. Include objective, milestone status, budget, KPI readiness, top risks, changes, decisions required, owners and due dates. |
| KNOWLEDGE CHECK | 1. How does decision authority differ from consultation? 2. Which information belongs in an executive status report? 3. What conditions should trigger formal escalation? |