PROFESSIONAL COURSE SERIES

MARKETING PROJECT

MANAGEMENT

| LECTURE 12 | 90-DAY IMPLEMENTATION ROADMAP |
| --- | --- |

COURSE POSITIONING

Strategy  |  Governance  |  Delivery  |  Measurement  |  Applied Learning

| PREPARED FOR | Ahmed Labib |
| --- | --- |
| EDITION | Lecture-Based Professional Course |
| ISSUE DATE | July 2026 |

A standalone lecture from the premium Marketing Project Management professional course.

CONFIDENTIAL  |  PROFESSIONAL LEARNING MATERIAL

# LECTURE 12  |  90-DAY IMPLEMENTATION ROADMAP

Deploying a controlled pilot before scaling process and technology

| LECTURE 12 BRIEF ¦ 90 MINUTES |  |
| --- | --- |
| LEARNING OUTCOMES | 1. Sequence design, pilot and scale activities into a controlled 90-day program. 2. Define phase exit criteria, ownership, dependencies and measurable adoption outcomes. 3. Develop an indicative implementation budget and risk-adjusted rollout plan. |
| SESSION FLOW | 10 min roadmap logic ¦ 20 min Days 1–30 ¦ 20 min Days 31–60 ¦ 15 min Days 61–90 ¦ 15 min roadmap workshop ¦ 10 min review |
| APPLIED OUTPUT | Owned 90-day implementation plan with gates, budget and success criteria. |

Figure 3 — Recommended 90-day roadmap with design, pilot and scale phases.

## 12.1 Phase 1 — Design (Days 1–30)

| Work package | Deliverable | Exit criterion |
| --- | --- | --- |
| Scope and stakeholder alignment | Defined audience, campaign types, objectives and governance sponsor. | Leadership confirms target use cases and authority. |
| Process mapping | Current-state intake-to-closure workflow and pain-point analysis. | Major handoffs, delays, duplicate data and control gaps are documented. |
| Core templates | Charter, intake, status, risk, change, measurement and closeout templates. | Templates approved for pilot. |
| KPI and data design | KPI dictionary, event taxonomy, data owners and quality checks. | Measurement owner signs off. |
| Tool inventory | Systems, integrations, licenses, duplication and constraints. | Architecture baseline completed. |

## 12.2 Phase 2 — Controls and pilot (Days 31–60)

| Work package | Deliverable | Exit criterion |
| --- | --- | --- |
| Governance rules | Stage gates, tolerance thresholds, approval SLAs and change authority. | Decision rights approved. |
| Compliance and AI | Launch checklist, disclosure, privacy and AI-review controls. | Control owners approve pilot use. |
| Pilot campaign | One representative project managed through the full framework. | Baseline established and weekly control cycle operating. |
| Dashboard validation | Delivery, budget, outcome and data-quality dashboard. | Metrics reconcile to source systems. |
| Training | Role-based training for sponsor, PM, workstream, analytics and reviewers. | Users demonstrate required tasks. |

## 12.3 Phase 3 — Scale (Days 61–90)

| Work package | Deliverable | Exit criterion |
| --- | --- | --- |
| Pilot review | Benefits, friction, defects, adoption and lessons report. | Corrective actions agreed. |
| Template refinement | Updated standards and campaign-archetype variants. | Version 1.0 control pack approved. |
| Architecture decision | Target platform / integration model and vendor shortlist. | Business case and procurement plan approved. |
| Rollout plan | Team sequence, migration, training, support and governance schedule. | Owners and dates committed. |
| Maturity baseline | Capability score and 12-month improvement backlog. | Executive review completed. |

## 12.4 Illustrative implementation budget

The following figures are planning assumptions only. They must be replaced with local labor rates, vendor quotations, integration requirements and regulatory scope before approval.

| Cost element | Lean retrofit | Consolidated rollout | Governance-first transformation |
| --- | --- | --- | --- |
| Process design and templates | $4,000 | $8,000 | $15,000 |
| Analytics and KPI setup | $3,000 | $7,500 | $18,000 |
| Privacy / compliance design | $2,000 | $5,000 | $12,000 |
| AI governance and policy | $1,500 | $4,000 | $10,000 |
| Tool configuration / migration | $3,500 | $12,000 | $30,000 |
| Training and enablement | $2,000 | $5,000 | $12,000 |
| Contingency | $2,000 | $6,500 | $18,000 |
| Estimated total | $18,000 | $48,000 | $115,000 |

## Applied learning and assessment

| LECTURE 12 APPLICATION |  |
| --- | --- |
| APPLIED WORKSHOP | Create a 90-day roadmap for one pilot campaign. Define workstreams, owners, dependencies, phase exit gates, adoption metrics, training, data migration, governance forums and scale/no-scale decision criteria. |
| KNOWLEDGE CHECK | 1. Why should process design precede broad technology rollout? 2. What evidence is required to exit the pilot phase? 3. Which adoption and control metrics should be measured during implementation? |